## 說明
證明書及呈交項目核對清單 — EM-00-03 §3.7、§1.2、§1.3、§1.5、§1.6（及相關條款）
Certificates & Submission Items Checklist — EM-00-03 §3.7, §1.2, §1.3, §1.5, §1.6 (and related)
填寫說明：黃色底色為填寫欄；灰色底色為示例行（正式呈交前請刪除）；「規格要求」欄為規格原文，不得改動。
依據：WSD EM-00-03（2025 年 10 月版）、EM-00-01（2023 年 12 月版）、EM-02-05（2026 年 5 月版）。港德環保科技編製，非水務署官方表格；特別規格及合約文件優先。編製日期 2026-09-03。
依據條款
• EM-00-03 Oct 2025 §1.1 paras 4–5 (itemised spares/tools list unless otherwise specified; quantities per §1.2/1.3/1.6; softcopy at the same time)
• EM-00-03 Oct 2025 §1.2 Equipment Approval (contents; 1 hardcopy within 1 month; 3-week comment; true copy within 3 weeks; resubmission within 3 weeks; no ordering of manufacture before approval)
• EM-00-03 Oct 2025 §1.3 Drawing Approval (GA, sectional details, process schematics, civil modification works; individual equipment drawings within 1 month of equipment approval; EM-90-01; resubmit on change during manufacture; approval does not relieve responsibility)
• EM-00-03 Oct 2025 §1.5.1 / §1.5.2 Recommended Maintenance Tools and Spare Parts (information within 1 month of acceptance of equipment submission; (a) itemised prices, (b) manufacturer's model, reference number, names and contact information, (c) parts and items drawings; priced list with drawings; original component manufacturer details; tools list per equipment type)
• EM-00-03 Oct 2025 §1.6 Instruction Manuals (draft 1 set ≥1 month before delivery; EM-90-02; 3-week comment; 4 sets final within 1 month of delivery with record drawings, works test reports and certificates; PDF on CD-ROM / DVD-ROM / portable hard drive)
• EM-00-03 Oct 2025 §3.7 Certificates of Compliance and Origin ((a) Certificate of Compliance if required; (b) Certificate of Origin if required; (c) authenticated by authorised representatives; inaccurate or misleading information may lead to rejection)
• EM-00-03 Oct 2025 §2.7 (label proposal before manufacture), §3.1 (duplicate packing list before arrival), §4.1(4) / §4.2(8) (software licence evidence before delivery), §1.4 (IIB per EM-00-01), §2.10(2) (AS/NZS 4020 reports)
填寫須知
• 此表是「呈交進度總表」。請先在表頭填寫合約開工日期、設備批准日期及預計交貨日期，再按各條款的相對限期推算每項的到期日（例如：設備呈交及圖則呈交——除非另有規定——均為開工後一個月內；備品資料——設備呈交獲接納後一個月內；說明書草稿——交貨前最少一個月；定稿——交貨後一個月內）。
• 設備呈交（§1.2）須包括每項設備的牌子、型號、額定值、技術資料、技術文獻及製造商標準圖；硬本一份並同時提交軟本（§1.1）。獲批准或有條件批准後三星期內，須呈交一份已蓋章核證（certified true copy）並納入所有修訂的文本；未獲批准前不得訂購製造。
• 圖則（§1.3）的詳細要求載於 EM-90-01，說明書（§1.6）的詳細要求載於 EM-90-02；本清單只列 EM-00-03 的數量及時限，格式內容請另行對照該兩份規格。製造階段如有任何改動，已批准圖則須重新呈交。
• 備品清單（§1.5.1）須逐項標價，並附製造商型號、參考編號、製造商名稱及聯絡資料、零件圖；若組件由其他製造商生產，須列出原廠名稱、地址及原廠零件編號，並將同一資料納入操作及保養手冊。
• §3.7 的合規證明書及原產地證明書屬「如需要」（if required）項目，由工程師／項目經理決定是否要求；一經要求，證明書須由供應商或製造商的授權代表核證，內容如有不確或誤導可導致設備被拒收，填寫時務必與型錄及銘牌資料一致。
• 「狀況」欄請按實際往來更新，並保留每次呈交及批覆的參考編號及日期，方便日後追溯。

## Milestones 里程碑
里程碑日期（供推算限期）Milestone dates
Fill these first; due dates below are relative to them
填寫說明：黃色底色為填寫欄；灰色底色為示例行（正式呈交前請刪除）；「規格要求」欄為規格原文，不得改動。
合約開工日期 Commencement of Contract
設備批准日期 Equipment approval date
設備呈交獲接納日期 Acceptance of equipment submission
預計交貨日期 Delivery date
檢驗 / 見證測試日期 Inspection / witnessed test date

## Checklist 核對表
呈交項目核對表 Submission items checklist
EM-00-03 §1.1–§1.6, §2.7, §3.1, §3.7, §4.1; EM-00-01
填寫說明：黃色底色為填寫欄；灰色底色為示例行（正式呈交前請刪除）；「規格要求」欄為規格原文，不得改動。
Item no. | Clause reference (EM-00-03 Oct 2025 §…) | Submission / certificate item (as named in the clause) | Required content (quoted or itemised from the clause) | Quantity & format (hardcopy count; softcopy Y/N; certified true copy; stamp / authentication) | Due date rule (relative to milestone: commencement of Contract / equipment approval / acceptance of equipment submission / delivery) and calculated calendar date | Responsible party (Contractor / manufacturer / supplier / IIB) | Status (Not yet due / Submitted / Comments received / Conditional approval / Approved / Resubmitted / True copy forwarded) | Submission ref. no. & date; comment / approval ref. & date | Remarks (e.g. 'if required' items — Engineer / PM instruction ref.; 'unless otherwise specified' overrides from PS / Contract)
SECTION A — EQUIPMENT APPROVAL SUBMISSION (§1.2)
A1 |  | make, model and rating of each item
A2 |  | technical details
A3 |  | technical literature
A4 |  | manufacturer's standard drawings
A5 |  | Compliance Schedule (this kit, Doc 1)
A6 |  | Standards Comparison Table if other standards offered (Doc 2)
A7 |  | Manufacturer Qualifying Experience Statement (Doc 3)
A8 |  | Materials-in-contact checklist + AS/NZS 4020:2018 reports (Doc 4)
A9 |  | one hardcopy + softcopy (§1.1)
A10 |  | due: within 1 month after commencement of Contract unless otherwise specified
A11 |  | comment/approval expected within 3 weeks
A12 |  | certified true copy incorporating amendments within 3 weeks of approval / conditional approval
A13 |  | resubmission within 3 weeks of comments if not approved
A14 |  | confirmation: no ordering of manufacture before approval
SECTION B — DRAWING APPROVAL (§1.3)
B1 |  | general arrangement
B2 |  | sectional details
B3 |  | process schematic diagrams
B4 |  | necessary civil modification works
B5 |  | drawings for individual equipment (within 1 month of equipment approval)
B6 |  | format per EM-90-01
B7 |  | one copy within 1 month after commencement unless otherwise specified; 3-week cycle; certified true copy set within 3 weeks of approval; resubmission within 3 weeks
B8 |  | resubmission if any change during manufacturing stage
B9 |  | note: approval does not relieve Contractor's responsibility
SECTION C — INSTRUCTION MANUALS (§1.6)
C1 |  | draft manuals, 1 set, at least 1 month before delivery
C2 |  | content per EM-90-02
C3 |  | further information within 3 weeks of comments
C4 |  | final manuals, 4 sets, within 1 month from delivery, incorporating amendments, record drawings, works test reports and certificates
C5 |  | PDF files on CD-ROM / DVD-ROM / portable hard drive
C6 |  | priced spare parts list and original component manufacturer information included in the O&M manuals (§1.5.1)
SECTION D — RECOMMENDED SPARES AND TOOLS (§1.5)
D1 |  | itemised list of recommended maintenance tools and spares (§1.1)
D2 |  | spares information within 1 month from acceptance of equipment submission: (a) detailed breakdown list of spares complete with itemised prices; (b) details of manufacturer's model, reference number, manufacturers' names and contact information; (c) parts and items drawings
D3 |  | one set of priced spare parts list with drawings / diagrams giving part numbers, nomenclature and location of components
D4 |  | for bought-in components: name and address of original component manufacturer and original part numbers
D5 |  | tools: complete set specified per equipment type; box labelled; tool list affixed inside lid; new and unused on handover
Spares/tools sub-table columns: Item
Part no. (supplier)
Original manufacturer & original part no.
Description / purpose
Recommended qty
Unit price
Currency / validity
Drawing ref.
Lead time
SECTION E — CERTIFICATES (§3.7)
E1 |  | Certificate of Compliance (if required) — obtained from manufacturer; states compliance with the requirements in this contract; authenticated by authorised representative of supplier / manufacturer
E2 |  | Certificate of Origin (if required) — country, state, name and address of the source, supplier or manufacturer as appropriate; authenticated
E3 |  | record of Engineer / Project Manager instruction requiring the certificate
E4 |  | authentication details: signatory name, position, date, company stamp
Certificate sub-table columns: Certificate type
Item / model / serial or batch
Issuer
Country / state
Signatory & position
Date
Ref. no.
Attached Y/N
SECTION F — OTHER RELATED SUBMISSIONS
F1 |  | label / nameplate proposal (style, material, inscription, location, fixing) for approval before manufacture (§2.7)
F2 |  | IIB nomination (Doc 6) and IIB documents (§1.4 / EM-00-01)
F3 |  | duplicate packing list before arrival of equipment (§3.1)
F4 |  | alternative packing method for tall / bulky items for approval (§3.2)
F5 |  | documentary evidence of all software licences prior to equipment delivery (§4.1(4), §4.2(8))
F6 |  | works test reports and certificates for inclusion in final manuals (§1.6)

## Spares 備件及工具
備件及工具子表 Spares & tools sub-table
EM-00-03 §1.5.1 (a)(b)(c), §1.5.2
填寫說明：黃色底色為填寫欄；灰色底色為示例行（正式呈交前請刪除）；「規格要求」欄為規格原文，不得改動。
項目 Item | 零件編號（供應商）Part no. | 原廠及原廠零件編號 Original manufacturer & part no. | 描述 / 用途 Description | 建議數量 Recommended qty | 單價 Unit price | 貨幣 / 有效期 Currency / validity | 圖則參考 Drawing ref. | 交貨期 Lead time
（例）Reagent set (free chlorine), 1 year | RG-100 | Maker A / RG-100 | DPD reagent | 4 |  | HKD / 90 days | DWG-05 | 6 weeks

## Certificates 證明書
證明書子表 Certificates sub-table
EM-00-03 §3.7 (if required); authenticated by authorised representatives
填寫說明：黃色底色為填寫欄；灰色底色為示例行（正式呈交前請刪除）；「規格要求」欄為規格原文，不得改動。
證明書類別 Certificate type | 項目 / 型號 / 序號或批號 Item / model / serial | 發出者 Issuer | 國家 / 州 Country / state | 簽署人及職位 Signatory & position | 日期 Date | 參考編號 Ref. no. | 已附 Attached (Y/N)
（例）Certificate of Compliance | Analyser model X, S/N 001 | Maker A | Country | Name, QA Manager | 2026-01-01 | CoC-001 | Y